## Index
Index
Policy Development
Select lead employee for project management/implementation/monitoring
Develop workgroup for tobacco free campus (TFC) policy
Possible work group members:
Executive team member, MIS,Pharmacy, Operations, HR, Trainer, Medical Records, Marketing/Communications, Facilities, community stakeholders
Explore possible options for tobacco-free policy (w/assistance of TTTF team)
Reference toolkit resources for sample tobacco-free worksite policies
Contact TTTF staff for technical assistance with crafting policy language
Create tobacco-free campus policy that includes organization TFC date and procedures for ongoing surveillance, monitoring, HR processes, and quarterly reporting
Review draft tobacco-free worksite policy against other LMHA policies (MIS, HR)
Submit draft tobacco-free worksite policy using existing P&P process
Organizational Preparation
Create online survey to email to employees and paper (possibly electronic) survey for consumers
Email survey to all employees and a segment of consumers to gather baseline information
As soon as policy is signed, communicate the new policy to all employees, community partners, consumers, and other vested groups and outline upcoming process to become a TFC (communication will be an ongoing process between now and effective TFC date)
Internal communication can include: email blast, staff meetings, newsletters, staff training, interoffice memos, screensavers, table tents
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Create and select language and graphics for internal and external signage & promotional materials
Take inventory of number of external signs needed
Meet with HR regarding NRT/medications covered under health benefits and, if possible, provide coverage for cessation aids not covered by insurance
Meet with MIS to integrate tobacco use assessment into EMR
Meet with MIS to intergrate coding and billing for tobacco cessation services into EMR
Meet with Pharmacy director regarding process and procedures to provide NRT to consumers and employees
Create signage informing employees, consumers and visitors of new TFC policy for waiting areas, break rooms, restrooms, etc.
Begin process to have permenant signs produced – work with facilities and sign company on installation before quit date
Design and order all promotional materials for policy implementation (water bottles, stress balls/hearts, sticky notes, t-shirts, buttons, hand sanitizers, etc.)
Continue to communicate TFC policy and release results from baseline survey to all employees and consumers
Communicate tobacco cessation resources and services available to employees and consumers
Continue to commuicate TFC policy to all community partners and other vested groups
Begin ordering all print materials for policy education - e.g. TFC reminder cards, training materials for employees, hand outs for consumers, tobacco cessation resources/materials, quit date celebration signage, etc.
Select and order new trash receptacles, if needed
Revise contracts with vendors, if needed, and communicate policy with all vendors
Create website (internal and external) with information on policy and cessation resources
TUA integrated in EMR
Commuicate TUA integration into EMR, provide training on how to document tobacco use in EMR
Meet with various departments/units/teams to educate on TFC policy, TUA, and cessation resources
Solicit questions/concerns/comments about policy and post on website & Q&A emails
Incorporate tobacco-free worksite policy information into New Employee Orientation
Create employee TFC policy acknowledgment statement (have all current and new employees sign statement)
Distribute all print materials to all various departments/units/teams
Email Q&A’s to employees about policy and cessation resources
Begin to install permenant signage outside – ensure signage is in place prior to implementation date
Remove all cigarette receptacles – install new trash receptacles, if had ash trays on them
Policy Implementation
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Celebration at each site – wear buttons/t-shirts, distribute promotional materials to consumers, visitors, etc.
Ensure that supervisors are enforcing the TFC policy
Bring employee violations to supervisors attention – address with employee
Ensure trash receptacles and permanent signage are in place at all sites
Ashtrays are removed from all sites
Distribute NRT to all consumers interested in quitting
Begin to assess all consumers for tobacco use
Program Monitoring and Evaluation
Ensure supervisors are enforcing TFC policy
Bring employee violations to supervisors attention
Continue to inform employees on TFC policy, compliance concerns and updates, highlight cessation opportunites and successful quit efforts
Conduct chart audits to ensure TUA is being completed
Conduct chart audit for cessation referral documentation and NRT/medication assistance
Conduct environmental scan of grounds and have conversations with employees about TFC policy and compliance issues
Follow-up point prevalence online survey for employees
Follow-up point prevalence survey (same method as initial survey) for consumers
Tobacco Free Campus and Tobacco Cessation Program Index

## Policy Development
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date
Select employee lead for TFC project and develop workgroup
Example of work group composition: Project Lead, Executive Member, MIS, Pharmacy, Operations, HR, Training, Medical Records, Marketing/Communications, Facilities, community stakeholders,
Explore possible options for tobacco-free policy (w/assistance of TTTF team)
Reference toolkit resources for sample tobacco-free worksite policies
Contact TTTF staff for technical assistance with crafting policy language
Create tobacco-free campus policy that includes organization TFC date and procedures for ongoing surveillance, monitoring, HR processes, and quarterly reporting
Review draft tobacco-free worksite policy against other LMHA policies (MIS, HR)
Submit draft tobacco-free worksite policy using existing P&P process
Tobacco Free Campus Policy Development Timeline

## Organizational Preparation
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date
Create online survey to email to employees and paper (possibly electronic) survey for consumers
Email survey to all employees and a segment of consumers to gather baseline information
As soon as policy is signed, communicate the new policy to all employees, community partners, consumers, and other vested groups and outline upcoming process to become a TFC (communication will be an ongoing process between now and effective TFC date)
Internal communication can include: email blast, staff meetings, newsletters, staff training, interoffice memos, screensavers, table tents
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Create and select language and graphics for internal and external signage & promotional materials
Take inventory of number of external signs needed
Meet with HR regarding NRT/medications covered under health benefits and, if possible, provide coverage for cessation aids not covered by insurance
Meet with MIS to integrate tobacco use assessment into EMR
Meet with MIS to integrate coding and billing for tobacco cessation services into EMR
Meet with Pharmacy director regarding process and procedures to provide NRT to consumers and employees
Create signage informing employees, consumers and visitors of new TFC policy for waiting areas, break rooms, restrooms, etc.
Begin process to have permanent signs produced – work with facilities and sign company on installation before quit date
Design and order all promotional materials for policy implementation (water bottles, stress balls/hearts, sticky notes, t-shirts, buttons, hand sanitizers, etc.)
Continue to communicate TFC policy and release results from baseline survey to all employees and consumers
Communicate tobacco cessation resources and services available to employees and consumers
Continue to communicate TFC policy to all community partners and other vested groups
Begin ordering all print materials for policy education - e.g. TFC reminder cards, training materials for employees, hand outs for consumers, tobacco cessation resources/materials, quit date celebration signage, etc.
Select and order new trash receptacles, if needed
Revise contracts with vendors, if needed, and communicate policy with all vendors
Create website (internal and external) with information on policy and cessation resources
TUA integrated in EMR
Communicate TUA integration into EMR, provide training on how to document tobacco use in EMR
Meet with various departments/units/teams to educate on TFC policy, TUA, and cessation resources
Solicit questions/concerns/comments about policy and post on website & Q&A emails
Incorporate tobacco-free worksite policy information into New Employee Orientation
Create employee TFC policy acknowledgment statement (have all current and new employees sign statement)
Distribute all print materials to all various departments/units/teams
Email Q&A’s to employees about policy and cessation resources
Begin to install permanent signage outside – ensure signage is in place prior to implementation date
Remove all cigarette receptacles – install new trash receptacles, if had ash trays on them
Tobacco Free Campus Organizational Preparation

## Policy Implementation
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date | One week
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Celebration at each site – wear buttons/t-shirts, distribute promotional materials to consumers, visitors, etc.
Ensure that supervisors are enforcing the TFC policy
Bring employee violations to supervisors attention – address with employee
Ensure trash receptacles and permanent signage are in place at all sites
Ashtrays are removed from all sites
Distribute NRT to all consumers interested in quitting
Begin to assess all consumers for tobacco use
Tobacco Free Campus Policy Implementation

## Monitoring and Evaluation
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date | One week | One month | Three months | Six months | One Year
Ensure supervisors are enforcing TFC policy
Bring employee violations to supervisors attention
Continue to inform employees on TFC policy, compliance concerns and updates, highlight cessation opportunites and successful quit efforts
Conduct chart audits to ensure TUA is being completed
Conduct chart audit for cessation referral documentation and NRT/medication assistance
Conduct environmental scan of grounds and have conversations with employees about TFC policy and compliance issues
Follow-up point prevalence online survey for employees
Follow-up point prevalence survey (same method as initial survey) for consumers
Tobacco Free Campus Monitoring and Evaulation

## Complete Timeline
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date | One week | One month | Three months | Six months | One Year
Select employee lead for TFC project and develop workgroup
Example of work group composition: Project Lead, Executive Member, MIS, Pharmacy, Operations, HR, Training, Medical Records, Marketing/Communications, Facilities, community stakeholders,
Explore possible options for tobacco-free policy (w/assistance of TTTF team)
Reference toolkit resources for sample tobacco-free worksite policies
Contact TTTF staff for technical assistance with crafting policy language
Draft tobacco-free campus policy that includes organization TFC date and procedures for ongoing surveillance, monitoring, HR processes, and quarterly reporting
Review draft tobacco-free worksite policy against other LMHA policies (MIS, HR)
Submit draft tobacco-free worksite policy using existing P&P process
Create online survey to email to employees and paper (possibly electronic) survey for consumers
Email survey to all employees and a segment of consumers to gather baseline information
As soon as policy is signed, communicate the new policy to all employees, community partners, consumers, and other vested groups and outline upcoming process to become a TFC (communication will be an ongoing process between now and effective TFC date)
Internal communication can include: email blast, staff meetings, newsletters, staff training, interoffice memos, screensavers, table tents
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Create and select language and graphics for internal and external signage & promotional materials
Take inventory of number of external signs needed
Meet with HR regarding NRT/medications covered under health benefits and, if possible, provide coverage for cessation aids not covered by insurance
Meet with MIS to integrate tobacco use assessment into EMR
Meet with MIS to intergrate coding and billing for tobacco cessation services into EMR
Meet with Pharmacy director regarding process and procedures to provide NRT to consumers and employees
Create signage informing employees, consumers and visitors of new TFC policy for waiting areas, break rooms, restrooms, etc.
Begin process to have permenant signs produced – work with facilities and sign company on installation before quit date
Design and order all promotional materials for policy implementation (water bottles, stress balls/hearts, sticky notes, t-shirts, buttons, hand sanitizers, etc.)
Continue to communicate TFC policy and release results from baseline survey to all employees and consumers
Communicate tobacco cessation resources and services available to employees and consumers
Continue to commuicate TFC policy to all community partners and other vested groups
Begin ordering all print materials for policy education - e.g. TFC reminder cards, training materials for employees, hand outs for consumers, tobacco cessation resources/materials, quit date celebration signage, etc.
Select and order new trash receptacles, if needed
Revise contracts with vendors, if needed, and communicate policy with all vendors
Create website (internal and external) with information on policy and cessation resources
TUA integrated in EMR
Commuicate TUA integration into EMR, provide training on how to document tobacco use in EMR
Meet with various departments/units/teams to educate on TFC policy, TUA, and cessation resources
Solicit questions/concerns/comments about policy and post on website & Q&A emails
Incorporate tobacco-free worksite policy information into New Employee Orientation
Create employee TFC policy acknowledgment statement (have all current and new employees sign statement)
Distribute all print materials to all various departments/units/teams
Email Q&A’s to employees about policy and cessation resources
Begin to install permenant signage outside – ensure signage is in place prior to implementation date
Remove all cigarette receptacles – install new trash receptacles, if had ash trays on them
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Celebration at each site – wear buttons/t-shirts, distribute promotional materials to consumers, visitors, etc.
Ensure that supervisors are enforcing the TFC policy
Bring employee violations to supervisors attention – address with employee
Ensure trash receptacles and permanent signage are in place at all sites
Ashtrays are removed from all sites
Distribute NRT to all consumers interested in quitting
Begin to assess all consumers for tobacco use
Ensure supervisors are enforcing TFC policy
Bring employee violations to supervisors attention
Continue to inform employees on TFC policy, compliance concerns and updates, highlight cessation opportunites and successful quit efforts
Conduct chart audits to ensure TUA is being completed
Conduct chart audit for cessation referral documentation and NRT/medication assistance
Conduct environmental scan of grounds and have conversations with employees about TFC policy and compliance issues
Follow-up point prevalence online survey for employees
Follow-up point prevalence survey (same method as initial survey) for consumers
Tobacco Free Campus Complete Timeline

## TFC Implementation Timeline
TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date
Develop work group and select employee lead for project
=--Work group compromised of: list various possible members
Explore possible options for tobacco-free policy (w/assistance of TTTF team)
Create tobacco-free campus policy that includes organization TFC date and procedures for ongoing surveillance, monitoring, HR processes, and quarterly reporting
Review draft tobacco-free worksite policy against other LMHA policies (MIS, HR)
Submit draft tobacco-free worksite policy using existing P&P process
Survey all employees and consumers to gather baseline information
As soon as policy is in effect, communicate the new policy to all employees, community partners, consumers, and other vested groups (communication will be an ongoing process between now and effective TFC date) e.g., email blast, staff meetings, newsletters, staff training, interoffice memos, signage informing of new policy (internally and externally), screensavers, table tents
Create media/publicity on TFC policy adoption, community notices, and quit date - celbrate successful quit stories
Select language and graphics for internal and external signage & promotional materials
Take inventory of number of external signs that will be needed
Begin process to have signs produced – work with facilities about installation
Create signage informing employees, consumers and visitors of new TFC policy for waiting areas, break rooms, restrooms, etc.
Design and order all promotional materials for policy implementation (water bottles, stress balls/hearts, sticky notes, t-shirts, buttons, hand sanitizers, etc.)
Continue to communicate policy to all employees, community partners, consumers, and other vested groups – including cessation resources and services available
Begin ordering all print materials for policy education
Select and order new trash receptacles, if needed
Meet with various departments/units/teams to educate on policy
Revise contracts with vendors, if needed, and communicate policy with all vendors
Create website (internal and external) with information on policy and cessation resources
Continue to communicate policy information – include any updates | [7 empty] | add training for staff for assessing/talking w consumer for tobacco
Solicit questions/concerns/comments about policy and post on website & Q&A emails | [7 empty] | MIS tobacco code training
Create employee TFC policy acknowledgment statement (have all current and new employees sign statement)
Incorporate tobacco-free worksite policy information into New Employee Orientation
Distribute all print materials to all various departments/units/teams
Email Q&A’s about policy and cessation resources
Begin to install signage outside – ensure signage is in place prior to implementation date
Remove all cigarette receptacles – install new trash receptacles, if had ash trays on them
Actively ensure that supervisors are enforcing the policyActively address tobacco use on grounds
Bring employee violations to supervisors attention – address with employee
Celebration at each site – wear buttons/t-shirts, distribute promotional materials to consumers, visitors, etc.
assess every consumer coming in for tobacco use
Tobacco Free Campus Policy Implementation Timeline

## TFC PostImplementation Timeline
Activity | Quit date | One week | One month | Three months | Six months | One Year
Actively ensure that supervisors are enforcing the policy
Bring employee violations to supervisors attention – address with employee
Celebration at each site – where buttons/t-shirts, give out promotional materials to consumers, visitors, etc.
Media/publicity to community (press releases, celebration of successful quit efforts, etc.)
Using the provided monitoring checklist and document with pictures, conduct comprehensive environmental scan of grounds and conversations with employees
Continue email blasts to employees on policy (include info on employee and consumer resources)
Provide Q&A from employees in emails and on website
Survey all employees to gauge resistance, acceptance, use rates, interest in cessation services, seek input, problems
Celebrate one year milestone for TFC, highlight successful quit efforts
Assess tobacco use rates among employees and consumers compare to intial assessment data
Tobacco Free Campus Policy
Post-Implementation Timeline

## Consumer Cessation Timeline
Activity | Six Months | Four months | Two months | One month | Quit Date | Ongoing
Assess needs/services provided (prior to tobacco-free policy implementation)
Assess tobacco use rate among consumers (approximate rate)
Assess percentage of consumers who would like to quit (if available)
Review/evaluate clinical protocols/procedures to ask, assess and refer consumers for cessation services
What are current protocols/procedures? Who does what and when do they do it?
Are protocols/procedures standard across agency? Assess which unit are asking consistently and which units need improvement.
Review and revise protocols to document tobacco in EMR/HER or paper documentation to make process easy and efficient for staff and consumer.
Review and revise referral process for tobacco cessation services.
Review and update all cessation services available to consumers.
Review/evaluate medications available to consumers to assist with quit attempt.
Prescription cessation medications (bupropion/varenicline/nicotine inhaler/nicotine nasal spray) available to consumers through insurance or health plans?
Nicotine patch/gum/lozenges available to consumers through insurance or health plans?
Determine nicotine replacement distribution process and procedures to clients? Storage of NRT?
Determine initial amount of nicotine replacement needed for clients, place order with CPRIT staff
Provide NRT to clients and order additional NRT products through direct NRT contact | [6 empty] | ???????
Are individual/group cessation counseling available to consumers through agency?
Research outside cessation services/resources available to consumers (e.g. QuitLine, American Lung Assoc., American Cancer Society, etc.)
Communicate cessation services (prior to and after tobacco-free policy implementation)
Communicate cessation services to clients, prior to (if possible) and in conjunction with the tobacco-free campus policy
Provide training on tobacco use screening and referral resources at staff meetings, staff training, new employee orientation
List client referral resources and cessation services in employee newsletter, tobacco website on Intranet, screensavers
Place flyers in waiting areas and common areas educating about tobacco-free policy and cessation resources that are available
Media/publicity on cessation service available to clients (press releases, celebration of successful quit efforts, etc.)
Community/regional partnerships
Local agencies (FQHC, Nicotine Anonymous, health department, cancer/heart disease prevention agencies, etc.)
Incorporate tobacco cessation into community wellness programs (exercise – YMCA, health clubs; nutrition/diet – internal/external programs/WIC; smoke-free housing initiatives)
Education/outreach to community
Benefits of quitting tobacco
Financial benefits of quitting
Health effects from secondhand smoke on family, especially children
Promote smoke-free homes and cars
Tobacco Cessation Program
Implementation Timeline